## Sheet1
Test Case ID | Module | Test Case | Expected Result | Actual Result | Status | Bug ID | Remarks
TC-LOGIN-001 | Login | Login with valid credentials | Dashboard should open | Dashboard opened successfully | PASS | — | Valid login successful
TC-LOGIN-002 | Login | Login with invalid username | Error message should appear |  | NOT EXECUTED | — | Execute during testing
TC-LOGIN-003 | Login | Login with invalid password | Error message should appear |  | NOT EXECUTED | — | Execute during testing
TC-LOGIN-004 | Login | Login with blank username | Username validation should appear |  | NOT EXECUTED | — | Execute during testing
TC-LOGIN-005 | Login | Login with blank password | Password validation should appear |  | NOT EXECUTED | — | Execute during testing
TC-LOGIN-006 | Login | Login with blank username and password | Required field validation should appear |  | NOT EXECUTED | — | Execute during testing
TC-LOGIN-007 | Login | Verify password is masked | Password should be hidden while typing |  | NOT EXECUTED | — | Execute during testing
TC-DASH-001 | Dashboard | Verify dashboard loads after login | Dashboard should load successfully |  | NOT EXECUTED | — | Execute during testing
TC-DASH-002 | Dashboard | Verify navigation menu is displayed | Navigation menu should be visible |  | NOT EXECUTED | — | Execute during testing
TC-DASH-003 | Dashboard | Verify user profile/menu | User profile/menu should be accessible |  | NOT EXECUTED | — | Execute during testing
TC-DASH-004 | Dashboard | Verify dashboard widgets | Dashboard widgets should display correctly |  | NOT EXECUTED | — | Execute during testing
TC-EMP-001 | Employee Management | View employee list | Employee list should be displayed |  | NOT EXECUTED | — | Execute during testing
TC-EMP-002 | Employee Management | Open Add Employee page | Add Employee page should open |  | NOT EXECUTED | — | Execute during testing
TC-EMP-003 | Employee Management | Add employee with valid data | New employee should be created |  | NOT EXECUTED | — | Execute during testing
TC-EMP-004 | Employee Management | Add employee with blank required fields | Validation messages should appear |  | NOT EXECUTED | — | Execute during testing
TC-EMP-005 | Employee Management | Edit employee information | Employee details should be updated |  | NOT EXECUTED | — | Execute during testing
TC-EMP-006 | Employee Management | Cancel employee edit | Changes should not be saved after cancellation |  | NOT EXECUTED | — | Execute during testing
TC-EMP-007 | Employee Management | Delete employee | Selected employee should be removed |  | NOT EXECUTED | — | Execute during testing
TC-EMP-008 | Employee Management | Cancel employee deletion | Employee should remain after cancelling deletion |  | NOT EXECUTED | — | Execute during testing
TC-EMP-009 | Employee Management | Verify Employee ID field | Employee ID should accept valid input |  | NOT EXECUTED | — | Execute during testing
TC-EMP-010 | Employee Management | Verify employee details after creation | Saved employee details should be displayed correctly |  | NOT EXECUTED | — | Execute during testing
TC-SEARCH-001 | Employee Search | Search employee by valid name | Matching employee should appear |  | NOT EXECUTED | — | Execute during testing
TC-SEARCH-002 | Employee Search | Search employee by invalid name | No matching employee should appear |  | NOT EXECUTED | — | Execute during testing
TC-SEARCH-003 | Employee Search | Search with blank fields | System should handle blank search correctly |  | NOT EXECUTED | — | Execute during testing
TC-SEARCH-004 | Employee Search | Reset employee search | Search filters should be cleared |  | NOT EXECUTED | — | Execute during testing
TC-LEAVE-001 | Leave Management | Open Leave List | Leave list should be displayed |  | NOT EXECUTED | — | Execute during testing
TC-LEAVE-002 | Leave Management | Open Apply Leave page | Apply Leave page should open |  | NOT EXECUTED | — | Execute during testing
TC-LEAVE-003 | Leave Management | Apply leave with valid data | Leave request should be submitted |  | NOT EXECUTED | — | Execute during testing
TC-LEAVE-004 | Leave Management | Apply leave with missing required data | Validation should appear |  | NOT EXECUTED | — | Execute during testing
TC-LEAVE-005 | Leave Management | Verify leave status | Submitted leave should show the correct status |  | NOT EXECUTED | — | Execute during testing
TC-LOGOUT-001 | Logout | Logout from application | User should be logged out successfully |  | NOT EXECUTED | — | Execute during testing
TC-LOGOUT-002 | Logout | Access protected page after logout | User should be redirected to login or denied access |  | NOT EXECUTED | — | Execute during testing