## Bug Tracker
Bug ID | Module | Summary | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Environment | Reported Date | Closed Date | Assignee | Notes
BUG-001 | Login | App accepts SQL injection string in username field | 1. Go to Login page 2. Enter ' OR '1'='1 in username 3. Enter any password 4. Click Login | Login should be rejected with invalid credentials error | User is logged in / app throws server error | Critical | P1 | Closed | Chrome 128 / Windows 11 | 2026-08-01 | 2026-08-04 | QA - You | Security bug, retested and verified fixed
BUG-002 | Cart | Quantity field accepts negative numbers | 1. Add item to cart 2. Open cart 3. Set quantity to -2 4. Click Update | Should reject negative quantity or reset to 1 | Cart total becomes negative | High | P1 | Reopened | Chrome 128 / Windows 11 | 2026-08-01 |  | QA - You | Fix broke on retest, reopened
BUG-003 | Checkout | Order confirms with empty shipping address | 1. Add item to cart 2. Proceed to checkout 3. Leave address blank 4. Click Place Order | Form should show validation error | Order is placed successfully with no address | High | P1 | Open | Firefox 130 / Windows 11 | 2026-08-02 |  | Unassigned
BUG-004 | Search | Search returns no results for valid product name with trailing space | 1. Go to Search 2. Type 'laptop ' (trailing space) 3. Press Enter | Should return laptop results, ignoring trailing whitespace | Returns 'No results found' | Medium | P2 | In Progress | Chrome 128 / Windows 11 | 2026-08-02 |  | Dev - Assigned
BUG-005 | Product Page | Price displayed without currency symbol on product detail page | 1. Open any product detail page | Price should show as $49.99 | Price shows as 49.99 | Low | P3 | Fixed | Chrome 128 / Windows 11 | 2026-08-03 | 2026-08-05 | Dev - Assigned | Awaiting QA retest
BUG-006 | Account | Password reset email not sent for unregistered email (info leak) | 1. Go to Forgot Password 2. Enter unregistered email 3. Submit | Generic message should show regardless of whether email exists | App explicitly says 'Email not found', revealing valid accounts | Medium | P2 | Ready for Retest | Chrome 128 / Windows 11 | 2026-08-03 |  | Dev - Assigned
BUG-007 | Cart | Cart icon count does not update after adding item | 1. Go to product page 2. Click Add to Cart | Cart icon badge should increment immediately | Badge stays at previous count until page refresh | Low | P3 | Open | Safari 17 / macOS | 2026-08-04 |  | Unassigned
BUG-008 | Checkout | Duplicate order placed on double-click of 'Place Order' | 1. Fill checkout form 2. Double-click Place Order button quickly | Only one order should be created | Two identical orders are created | Critical | P1 | Open | Chrome 128 / Windows 11 | 2026-08-04 |  | Unassigned
BUG-009 | Login | Session does not expire after logout when using browser back button | 1. Log in 2. Log out 3. Click browser Back button | User should be redirected to login page, session should be invalid | Previous logged-in page is shown from cache, session still appears active | Medium | P2 | Closed | Chrome 128 / Windows 11 | 2026-08-01 | 2026-08-05 | QA - You | Fixed with cache-control headers
BUG-010 | Search | Search suggestions dropdown overlaps page footer on small screens | 1. Go to Search bar 2. Start typing a product name 3. View suggestions dropdown | Dropdown should render above footer, fully visible | Dropdown is cut off / renders behind footer | Low | P4 | Closed | Chrome 128 / Windows 11 | 2026-08-02 | 2026-08-05 | Dev - Assigned | Minor CSS z-index fix
BUG-011 | Checkout | Invalid coupon code shows no error message | 1. Add item to cart 2. Go to checkout 3. Enter invalid coupon code 'ABC123' 4. Click Apply | Should show 'Invalid coupon code' error | Nothing happens, discount silently not applied | High | P2 | Closed | Firefox 130 / Windows 11 | 2026-08-02 | 2026-08-06 | Dev - Assigned | Verified fix in retest
BUG-012 | Cart | Cart badge count does not reset to 0 after removing last item | 1. Add 1 item to cart 2. Open cart 3. Remove the item | Cart icon badge should show 0 or disappear | Badge still shows previous count (1) | Medium | P3 | Closed | Chrome 128 / Windows 11 | 2026-08-03 | 2026-08-06 | Dev - Assigned
BUG-013 | Product Page | Product images show no loading state on slow connections | 1. Throttle network to Slow 3G (dev tools) 2. Open any product detail page | Should show a loading placeholder/skeleton while image loads | Blank white space shown until image fully loads, looks broken | Medium | P3 | Open | Chrome 128 / Windows 11 (throttled) | 2026-08-04 |  | Unassigned
BUG-014 | Account | Changing account email does not require password confirmation | 1. Log in 2. Go to Account Settings 3. Change email address 4. Save | Should require current password before allowing email change | Email is changed with no re-authentication | High | P1 | In Progress | Chrome 128 / Windows 11 | 2026-08-04 |  | Dev - Assigned | Security concern, escalated
BUG-015 | Checkout | Order confirmation page still accessible via back button after logout | 1. Complete an order 2. Log out 3. Click browser Back button | Should redirect to login, not show confirmation page again | Order confirmation page with order details is still visible | Medium | P2 | Fixed | Chrome 128 / Windows 11 | 2026-08-05 | 2026-08-06 | Dev - Assigned | Awaiting final QA retest
BUG-0XX | <module> | <one-line summary> | <numbered steps> | <what should happen> | <what actually happened> | Critical/High/Medium/Low | P1/P2/P3/P4 | Open | <browser/OS> | <yyyy-mm-dd> |  | <assignee> | <optional>

## Severity-Priority Guide
Severity | Definition | Example
Critical | App crash, data loss, security breach, blocks all use of core feature | SQL injection lets attacker log in as any user
High | Major feature broken, no workaround, but app doesn't crash | Checkout completes with no shipping address
Medium | Feature partially broken or has a workaround | Search misses results with trailing whitespace
Low | Cosmetic / minor annoyance, doesn't block usage | Missing currency symbol on price
Priority | Definition
P1 | Fix immediately, blocks release
P2 | Fix before release, high business impact
P3 | Fix soon, but can ship without it
P4 | Fix when convenient / backlog
Note: Severity = technical impact. Priority = business urgency. A cosmetic bug on the homepage banner (Low severity) can still be P1 if a client demo is tomorrow.

## Summary Dashboard
Bug Lifecycle States
Open -> In Progress -> Fixed -> Ready for Retest -> Closed
(If retest fails: Ready for Retest -> Reopened -> back to In Progress)
Metric | Count
Total Bugs Logged | 15
Open | 5
In Progress | 2
Fixed | 2
Ready for Retest | 1
Closed | 5
Reopened | 1
Critical Severity | 2
High Severity | 4
Medium Severity | 6
Low Severity | 3
P1 Priority | 5
These counts auto-update from the Bug Tracker sheet as you log real bugs. Delete the 8 sample rows once you have your own, or just keep adding below them.