## RTM
Req ID | Requirement Description | Module | Scenario ID(s) | Test Case ID(s) | Test Status | Defect ID(s) | Coverage
REQ_01 | User must be able to log in with valid credentials | Login | SC_01 | TC_001, TC_002 | Pass |  | Full
REQ_02 | System must reject invalid login attempts with a clear error | Login | SC_02 | TC_003, TC_004, TC_005 | Pass |  | Full
REQ_03 | User must be able to log out and end the session | Login | SC_03 | TC_006 | Pass |  | Full
REQ_04 | User must be able to initiate a password reset request | Login | SC_04 | TC_007 | Pass |  | Full
REQ_05 | Admin must be able to add a new employee record | PIM | SC_05 | TC_008, TC_009, TC_010 | Fail | BUG_001, BUG_003 | Partial
REQ_06 | Admin must be able to search/filter employee records | PIM | SC_06 | TC_011, TC_012 | Fail | BUG_004 | Partial
REQ_07 | Admin must be able to edit an employee's personal details | PIM | SC_07 | TC_013 | Pass |  | Full
REQ_08 | Admin must be able to delete an employee record | PIM | SC_08 | TC_014 | Pass |  | Full
REQ_09 | User must be able to apply for leave with valid dates | Leave | SC_09 | TC_015 | Pass |  | Full
REQ_10 | System must validate leave date ranges and mandatory fields | Leave | SC_10 | TC_016, TC_017 | Fail | BUG_002 | Partial
REQ_11 | User must be able to view and filter the leave list by status | Leave | SC_11 | TC_018 | Pass |  | Full
REQ_12 | Admin must be able to add a new system user | Admin | SC_12 | TC_019 | Pass |  | Full
REQ_13 | Admin must be able to add a new recruitment candidate | Recruitment | SC_14 | TC_020 | Fail | BUG_005 | Partial
Coverage Summary
Total Requirements | 13
Fully Covered & Passing | 9
Partially Covered (defect open) | 4